## Dashboard
Project CUCM: Purchasing and implementation
Description: This is a document resource overview for the IT Team for CUCM Purchasing and insltallation Plan
Owner: CISCO Team
Status: Final
Key Docs | Description
Situation Statement | Outlines The current State and helps define the problem or opportunity being addressed
SWOT Analysis | Strategic tool that identifies Orgnization's Strengths and Weaknesses, Opportunities and Threats, to aid in decision-making and planning.
Fishbone Diagram | Visual tool used to identify, organize, and analyze the potential causes of a specific problem.
Smart Goals | SMART goals are objectives that are Specific, Measurable, Achievable, Relevant, and Time-bound,
OKRs | OKRs (Objectives and Key Results) are a goal-setting framework that defines clear, ambitious objectives and measures success through specific, actionable key results.
Stakeholder Analysis | Process of identifying, assessing, and prioritizing individuals or groups with an interest in a project to understand their influence, expectations, and how best to engage with them.
Power Interest Grade | Categorization of stakeholders based on their level of power (influence over the project) and interest (concern about project outcomes), helping to prioritize engagement strategies.
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Project charter | An overview of the project, key elements and expectations
Project Schedule. | Detailed timeline that outlines the planned start and finish dates for each task, milestone, and phase of a project to ensure timely completion and effective resource allocation
Dependence Task | lists tasks in a project along with their relationships, identifying which tasks must be completed before others can start, thereby helping to clarify workflow and scheduling.
Critical Path | The longest sequence of dependent tasks in a project that determines the shortest possible completion time, with any delay in these tasks directly impacting the project's overall timeline.
Network Diagram | Visual representation of a project's activities and their interdependencies, illustrating the sequence of tasks and the critical path for project planning and management.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation

## Project Schedule.
CUCM Purchasing and implementation
Gantt Chart
TITLE: CUCM Purchasing and implementation | [6 empty] | COMPANY NAME: |  |  |  |  | Al Manara
PROJECT MANAGER: Tean Name | [6 empty] | CREATION DATE: |  |  |  |  | 20/10/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30
[7 empty] | November | [19 empty] | December | [22 empty] | Jan | [21 empty] | Feb | [19 empty] | March | [21 empty] | April | [21 empty] | May
[7 empty] | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T
1 | Finalize the design of CUCM (based on the customization of the system) | [5 empty] | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
1.1 | Architecture design approval after customization | IT | 01/11/2024 | 15/11/2024 | 10 | 0% | bar: November S 3 to November T 14
1.2 | Network design documentation | Vendor | 01/11/2024 | 08/11/2024 | 5 | 0% | bar: November S 3 to November T 7
1.3 | Customization of user interface based on BRD | Vendor | 09/11/2024 | 23/11/2024 | 10 | 0% | bar: November S 10 to November T 21
2 | Accomplish the installation of CUCM
2.1 | CUCM servers (UAT & Production) Installation | IT | 16/11/2024 | 30/11/2024 | 10 | 0% | bar: November S 17 to November T 28
2.2 | CUCM settings Configuration | Vendor | 24/11/2024 | 01/12/2024 | 5 | 0% | bar: November S 24 to December S 1
2.3 | Database Set up for CUCM | IT | 02/12/2024 | 08/12/2024 | 5 | 0% | bar: December M 2 to December S 8
2.4 | Set up and distribute IP phones and other end-user devices | IT | 02/12/2024 | 16/12/2024 | 10 | 0% | bar: December M 2 to December M 16
3 | Deliver the integration with CRM
3.1 | Integration architecture document | IT and vendor | 17/12/2024 | 31/12/2024 | 10 | 0% | bar: December T 17 to December T 31
3.2 | Implementation of APIs for communication between CUCM and CRM | IT and vendor | 01/01/2025 | 15/01/2025 | 5 | 0% | bar: Jan W 1 to Jan W 15
3.3 | Implement data mapping between CUCM and CRM | IT and vendor | 16/01/2025 | 23/01/2025 | 10 | 0% | bar: Jan T 16 to Jan T 23
4 | Test the CUCM and integration between CUCM and CRM
4.1 | Unit testing of configurations for CUCM | IT | 24/01/2025 | 31/01/2025 | 5 | 0% | bar: Jan S 26 to Jan T 30
4.2 | System integration testing | IT and vendor | 24/01/2025 | 2025-07-02 | 5 | 0% | bar: Jan S 26 to Feb W 5
4.3 | User acceptance testing | IT | 08/02/2025 | 22/02/2025 | 10 | 0% | bar: Feb T 6 to Feb T 20
5 | Users training
5.1 | Develop a training schedule that accommodates users' availability | IT | 23/02/2025 | 02/03/2025 | 10 | 0% | bar: Feb S 23 to March S 2
5.2 | Conduct training sessions or workshops to demonstrate CUCM features and functionalities | IT | 03/03/2025 | 17/03/2025 | 10 | 0% | bar: March M 3 to March M 17
5.3 | Provide clear user guides and documentation that users can reference after training | IT | 18/03/3035 | 25/03/2025 | 5 | 0% | bar: March T 18 to March T 25
5.4 | practice with users using CUCM in the UAT server | IT | 18/03/3035 | 25/03/2025 | 5 | 0% | bar: March T 18 to March T 25
5.5 | Gather feedback from users about the training effectiveness and CUCM system | End User | 26/03/2025 | 02/04/2025 | 5 | 0% | bar: March W 26 to April W 2
5.6 | Establish a support team for users for help or further training as needed | IT | 26/03/2025 | 02/04/2025 | 5 | 0% | bar: March W 26 to April W 2
6 | Migration from legacy system
6.1 | Backup all data from the legacy system | IT | 03/04/2025 | 10/04/2025 | 5 | 0% | bar: April T 3 to April T 10
6.2 | Transfer data from the legacy system to CUCM | IT and vendor | 11/04/2025 | 25/04/2025 | 10 | 0% | bar: April S 13 to April T 24
6.3 | Finalize testing the migrated data to ensure functionality and performance | IT and vendor | 26/04/2025 | 03/05/2025 | 10 | 0% | bar: April S 27 to May T 1
7 | Going live & Finalize the Handover process
7.1 | Conduct final testing to ensure the system is functioning as expected | IT | 04/05/2025 | 11/05/2025 | 5 | 0% | bar: May S 4 to May S 11
7.2 | transition to the live environment in the new system | IT and vendor | 12/05/2025 | 19/05/2025 | 5 | 0% | bar: May M 12 to May M 19
7.3 | Obtain formal sign-off from both the vendor and IT department to finalize the handover process | IT and vendor | 20/05/2025 | 27/05/2025 | 5 | 0% | bar: May T 20 to May T 27

## Project Schedule (hidden)
CUCM
Gantt Chart
TITLE: CUCM Purchasing and implementation | [6 empty] | COMPANY NAME: |  |  |  |  | Al Manara
PROJECT MANAGER: Tean Name | [6 empty] | CREATION DATE: |  |  |  |  | 20/10/2024
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE | [29 empty] | ask chat GPT to convert it to outcome
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Define System Vendor | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Make A request for proposal (RFP) | PM |  |  |  | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Bid Announcement | PM |  |  |  | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Receive Bids and evaluate technical proposals | PM |  |  |  | 0% | bar: MARCH M 15 to MARCH F 26
1.4 | Evaluate financial proposals | Financial team |  |  |  | 0% | bar: MARCH M 15 to MARCH F 26
1.5 | Confirm Vendor Selection and send approval email | PM |  |  |  | 0% | bar: MARCH M 15 to MARCH F 26
1.6 | Prepare contracting | Contracting Team |  |  |  | 0% | bar: MARCH M 29 to APRIL F 9
1.7 | Sign contract and kick off implementation | PM |  |  |  | 0% | bar: MARCH M 29 to APRIL F 9
2 | Preparation for Installation
2.1 | Verify server readiness (physical/virtual) for CUCM installation. | PM |  |  |  | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Ensure network connectivity between CUCM server and voice gateways. | IT Team |  |  |  | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Confirm availability of required licenses and software versions. | IT Team |  |  |  | 0% | bar: APRIL M 19 to APRIL F 30
3 | Finish Installation
3.1 | Software server UAT & Production configration | IT Team |  |  |  | 0% | bar: MAY M 3 to MAY F 14
3.2 | Sync CUCM with the database and ensure data integrity | IT Team |  |  |  | 0% | bar: MAY M 17 to MAY F 28
3.3 | system customization | PM/IT Team | bar: MAY M 17 to MAY F 28
3.4 | Conduct initial testing of the CUCM installation. | IT Team | bar: MAY M 17 to MAY F 28
3.5 | testing and evaluation of system | IT Team | bar: MAY M 17 to MAY F 28
3.6 | Perform test calls (internal and external) to verify system functionality | IT Team , PM |  |  |  | 0% | bar: MAY M 31 to JUNE F 11
4 | Finalize Integration with CRM
5 | Training For Users
5.1 | Get User tariniang material and user guid documents | PM | bar: MAY M 3 to MAY F 14
5.2 | training sessions for system users | PM | bar: MAY M 17 to MAY F 28
5.3 | Create a training program for technicians and staff | PM | bar: MAY M 31 to JUNE F 11

## Budget
Budget: CUCM Purchasing and implementation
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 1210000 | 0 | 1210000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | EGP/UNIT(S)
Milestone 1: Finalize the Design of CUCM (Customization)
Task 1: Architecture design approval after customization | 3 | 20 | 500 |  |  |  | 30000 |  | -30000
Task 2: Network design documentation | 1 | 10 | 500 |  |  |  | 5000 |  | -5000
Task 3: Design User Interface | [5 empty] | 200000 | 200000
[6 empty] | Total | 235000 | 0
Milestone 2: Accomplish the installation of CUCM
Task 1: CUCM servers (UAT & Production) Installation | 2 | 15 | 500 | 1 | 100000 |  | 115000 |  | -115000
Task 2: Set up and distribute IP phones and other end-user devices | 2 | 15 | 500 |  |  | 100000 | 115000 |  | -115000
Task3 :CUCM settings Configuration | 2 | 15 | 500 |  |  |  | 15000 |  | -15000
Task4 :Database Set up for CUCM | 2 | 15 | 500 |  |  | 50000 | 65000
[6 empty] | Total | 310000 | 0
Milestone 3: Deliver the Integration with CRM
Task 1: Implement APIs and data mapping between CUCM and CRM | 3 | 50 | 500 |  |  | 100000 | 175000 |  | -175000
[6 empty] | Total | 175000 | 0
Milestone 4: Test the CUCM and integration between CUCM and CRM
Task1: Test CUCM configrations and integration system | 2 | 20 | 500 |  |  |  | 20000 |  | -20000
Task2 : UAT User Acceptance Test | 3 | 20 | 500 |  |  |  | 30000
[6 empty] | Total | 50000 | 0
Milestone 5: Users training
Task1:Conduct training session and provide user guids and practice on UAT server | 3 | 60 | 500 |  |  | 100000 | 190000 |  | -190000
[6 empty] | Total | 190000 | 0
Milestone 6: Migration from legacy system
Task 1:Backup and transfer migrated data | 3 | 40 | 500 |  |  |  | 60000 |  | -60000
Task 2: Finalize testing the migrated data to ensure functionality and performance | 2 | 20 | 500 |  |  |  | 20000
[6 empty] | Total | 80000 | 0
Milestone 7: Going live & Finalize the Handover process
Task1:Obtain formal sign-off from both the vendor and IT department to finalize the handover process | [5 empty] | 100000 | 100000 |  | -100000
[6 empty] | Total | 100000 | 0
Reserve buffer | [6 empty] | 70000 |  | -70000
TOTAL | [6 empty] | 1210000 | 0

## Communication Plan
CUCM Purchasing and implementation - Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
IT Team & Vendor | Planning Meeting | Weekly | Project Manager | Every Sunday at 10 AM | In Person | Discuss and share task updates to make sure the team stays on track | [link to meeting agenda and notes]
Software and Equipment Vendor | Planning Meeting | One time | IT Team | One Week before starting installation; confirm date and time three days in advance | In Person | Check status of equipment delivery dates and ensure preparation is done | [link to vendor SoW]
Operation Team | Planning Meeting | One time | Project Manager | Also send reminders (via email) the day before each training | In Person | share Project Implementation updates with operation team and Communicate schedules, locations, and other necessary details of trainees
End Users | Training | Daily | IT Team | After UAT milestone is done | In Person | Providing users training for each department, other necessary details to trainees | [trainee email list]
End Users | Survey | One time | Project Manager | The first business day after trainings end, with two follow-up reminders | Email (from company address) | Post-training survey | [trainee email list]
IT Team Manager | Status Update | Weekly | Project Manager | Sunday at 2 PM | In Person | Update on Implementation status , ask questions, and get feedback
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | After Completion of UAT phase | Email (from individual address) | High-level information and general updates | [link to folder with training notes and survey results]

## RACI Chart
CUCM Purchasing and implementation - RACI CHART
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Project manager (IT) | Network Admin | Security Team | Operation Management | Vendor | Pmo Team | Call Center agents & Technicians | El Manara Investors | Finance Team
PHASE 1
Task/Deliverable
1. System Installation | A | R | R | I | R | C | I | I | I
2. Training for users, agents, and technicians | R | I | I | A | R | I | I | I | I
3. User manuals & guides for training sessions. | R | I | I | I | R | C | I | I | I
4. Warranty and system licences | A | I | I | I | R | I | I | I | I
5. Link the system with crm | A | C | C | I | R | C | I | I | I
6.Migration with the legacy system | A | I | I | I | R | C | I | I | I

## Dependence Task
Activity | Precedence | Duration
Start | 0 | 0
A | Start | 2W
D | A | 2W
F | D | 1W
B | Start | 1W
c | B | 2W
E | c | 1W
G | E | 2W
H | F&G | 2W
I | H | 2W
J | I | IW
K | J | IW
L | J | 2W
M | K&L | 2W
N | M | IW
o | N | 2W
p | o | IW
q | o | IW
S | P | IW
R | Q | IW
T | R | IW
U | T | 2W
V | U | IW
W | V | IW
X | W | IW
Y | X | IW
END | S&Y | 0